## Cover
Greater London Authority
Zero Carbon Accelerator
Solar PV Checklist - Template
Version: | 1 | Date: | 2026-02-19 | Purpose: | Template
Author: | SA, KU | Checker: | OH | Approver: | AW
Document Number: | GLA_ZCA_82559-MMD_ART-XX-XX-TMP-TMO-0004
This document is issued for the party which commissioned it and for specific purposes connected with the above-captioned project only. It should not be relied upon by any other party or used for any other purpose. Mott MacDonald, its sub-consultants and the Greater London Authority accept no responsibility for the consequences of this document being relied upon by any other party, or being used for any other purpose, or containing any error or omission which is due to an error or omission in data supplied to us by other parties

## Introduction
Introduction This document has been developed as part of the Greater London Authority (GLA) Zero Carbon Accelerator programme, which supports public sector organisations to accelerate the energy transition of their London buildings, delivering decarbonisation projects across the sector, including on and for NHS healthcare estates. Developed as part of a direct package of support provided by the Zero Carbon Accelerator to an NHS Trust, this document is intended as guidance/support for other organisations delivering solar PV installations and will be of particular use for other NHS Trusts and healthcare bodies. This document includes a checklist of activities that need to be completed across the RIBA stages as part of the development and delivery of a solar PV project. The solar PV Checklist tab acts as both a project check sheet and a project progress tracker. Caveats and Limitations This checklist guidance is provided for reference and support only and does not remove the need for project‑specific design development, site‑specific risk assessments, or compliance with current legislation, standards, and Trust policies. Each organisation remains responsible for ensuring that any solar PV project is delivered in accordance with its own governance arrangements and statutory obligations. Where conflicts arise, the more onerous requirement shall apply.
Abbreviations and Acronyms Used in Checklist
Acronym / Abbreviation | Term
ASHP | Air source heat pump
BMS | Building management system
CE | Conformité Européene, or European Conformity marking
COSHH | Control of substances hazardous to health
CPP | Construction phase plan
DC/AC | Direct current / alternating current
DHW | Domestic hot water
DNO | Distribution network operator
EICR | Electrical installation condition report
EV | Electric vehicle
H&S | Health and safety
HH | Half hourly
ICP | Independent connection provider
kW | Kilowatt
kWp | Kilowatt-peak
LAN | Local area network
LPS | Lightning protection systems
LV | Low voltage
MCS | Microgeneration Certification Scheme
MOP | Meter Operator
MV/HV | Medium voltage / high voltage
NICEIC | National Inspection Council for Electrical Installation Contracting
O&M | Operation and maintenance
PM | Project manager
POC | Point of connection
PPA | Power purchase agreement
PV | Photovoltaics
R&D | Refurbishment and demolition
RAMS | Risk Assessment Methodology Statement
RMU | Ring main unit
SEG | Smart Export Guarantee
SLD | Single line diagram
UKCA | UK Conformity Assessed

## Solar PV Checklist
Solar PV Project - Project Check Sheet & Progress Tracker
RIBA Stage | RIBA Stage Description | Activities |  | Site 1 | Site 2 | Site 3 | Site 4 | Site 5 | Overall Progress
1 | Preparation | Appoint Delivery team - project sponser, PM, PV Design Consultant | [7 empty] | List
|  | Data Collection | [7 empty] | Complete
|  |  | Energy Data - 12month HH Electricity data Preferred, or Monthly billing if HH not Available, 12month Energy bills, tariff type | [6 empty] | N/A
|  |  | Existing Electrical System: SLD, EICR Report, switchgear condition assessment (no outstanding rectification work required), retrofit bi-directional circuit breakers, non asbestos arc shields etc | [6 empty] | In Flight
|  |  | Existing Incoming Supply: Capacity Assessment, Existing Connection Agreement | [6 empty] | Behind
Conflict with other planned future planned works
Alignment with Estate Management Master Plan
Roof condition Assessment - latest Structural Survey, concerns fragile or asbestos roof materials
Outstanding Warranty Conditions on roofs
Site Plans/Drawings (accurate)
Asbestos Management Plan
Understand Project Objectives
Carbon Saving
Cost Saving
Resilience - security of supply
Capacity Building -future requirements for ASHP,EV Charging, heating of DHW, kitchen decarbonisation
Source of Funds and Conditions of project spend (milestone dates)
Project Governance . Approvals requirements at each stage
Overall aims - Export energy (SEG or PPA with 3rd party), or self consume and displace imported energy
2 | Concept Design | PV Modelling (remote feasibility)
Weather Data
Initial Panel Selection - including any sustainable procurement requirements (modern slavery, UKCA, CE marking)
Initial Invertor Selection - including any sustainable procurement requirements (modern slavery, UKCA, CE marking)
Panel Layout (configuration)
String Design
Roof orientation
Shading issues
Obstructions on roof
System Yield
Budget cost based industry benchmarks
System suitbalitity for battery storage
Estimated yield based on remote study
installed solar kWp
3 | Spatial Coordination | PV System (site survey)
Optimise system to meet objective and overcome constraints
Identify invertor locations - Wall space/Under Panels
Provisional Cable Runs
Frame Selection and panel mounting
Roof Penetrations allowed - Yes/No
Point of connection review
System integration
Lightning protection
Other onsite generation including Standby Generators
Fire Alarm System
IT Integration for metering and monitoring
Generation and Export Metering
Planning & Regulatory
Planning Pre Application
Glint and glare concerns
Conservation area
Listed Building
DNO Provisional Draft Budget Report
Design Risk Assessment
Safe Access for Installation
Safe Access for Maintenance
Impact of other Roof Furniture / Equipment
Bird Protection Strategy
Draft Programme - including Preconstruction period
Confirm funding is in place and approval process to release
Agree procument route
Tender Process for Design and Build contract or design only
Prepare Spectication & scope of supply
Create a tender list (suitabley experienced contractors)
Issue tender documents
Receive Tenders
Tender analysis , contractor interviews
Contractor appointment
Confirm milestone program, agree payment schedule, appoint contractor and onsite project manager
4 | Technical Design | Surveys
Structural Survey
Asbestos R & D Surveys - Roof, along Cable Routes, penetrations and Invertor Location
GPR Surveys for underground services if required
System Design
Finalise/Freeze Panel Layouts, Framing, String Design, Invertor Positions and Point of Connection
Cable sizing and Containment
Electrical Design
DC/AC Isolator Requirements
Circuit Protection Devices
G100 Export Limitation if required
Power ugrades - Transformer / RMU Design if POC is MV/HV
Controls Integration with other systems - Generators, Fire, BMS etc.
Planning & Regulatory
Planning Application / Certificate of Lawful Development
G99 / G98 Application to DNO
DNO approval
Grid Re-enforcement Required
Lease/Wayleaves and Other Legals for any new infrastructure
DNO Design for reinforcement and new connections
Contractor / ICP design for contestable works if required
Permanent safe access system if required
Lightning Protection
Design New LPS or Integration plan for Existing
Metering & Monitoring
Generation and Export Metering
Remote monitoring connections - 5G / Wi-Fi / LAN and license costs / duration
Assemble PCIP - Preconstruction Information Pack
Site location
Asbestos Management Plan & RD Surveys
Fire Strategy
Access Requirements / Hours
Transport limitations
Emergency Procedures
Contacts and responsibilities
Handover requirements including documentation format and contents of H&S File and O & M Manuals
Commissioning and Performance reporting - Agree protocol and duration
Agree procument route
Tender Process for Supply and install contract only
Prepare Spectication & scope of supply
Create a tender list (suitabley experienced contractors)
Issue tender documents
Receive Tenders
Tender analysis , contractor interviews
Contractor appointment
Confirm milestone program, agree payment schedule, appoint contractor and onsite project manager
5 | Manufacturing & Construction | Agree detail Construction Programme
Generate CPP - Construction Phase Health &Safety Plan
Hygiene facilities
Transport, Laydown and Storage Plan
Subcontractors
Induction Process
Emergency Rpecudures
Work Patterns
Coordination of work and Site Supervision
F10 Submission
Procure Long lead Items
Transformers / RMU / LV Switchgear if required
Solar Panels and invertors
Mounting Frames
Pre Works - Photo condition survey of work areas.
Pre-works - Validation of existing systems remaining after installation
Coordinaton
Client Service Interruption
Scaffolding
Overcladding required for skylights - Yes/No
Solar Panels and invertors
LPS if Required
Roof Fall Protection if required
Meter Operator (MOP) if new fiscal meter required
DNO / ICP if grid reinforcement required
Penetrations
Roof Penetrations - Fully sealed including compliance with any warranty
All Penetrations through Fire Compartments- agree standard for temporary fire stopping during construction
All Penetrations through Fire Compartments- Permanent Fire Stopping by an accredited specialist contractor to meet fire Strategy
Commissioning Plan - complete to agreed protocol
6 | Handover | Demonstration & Training (witness testing to include stakeholders)
Operational Verification
Start up /shutdown procedures - Routine & Emergency
Integration with other systems (simulation)
Basic fault identification and training
Remote Monitoring App
Documentation Required
H & S File (electronic)
H&S file review
H&S sign off
O & M Manual (electronic)
O & M Manual review
O & M Manual sign off
H & S File contents - Minimum
CPP
RAMS
COSHH
Planning permissions
DNO Connection Agreement
Residual risk register
plus O&M
O & M Manual - Minimum contents
Design basis and operations
As Fitted Mechanical Drawings for all systems installed
As Fitted Electrical - SLD individual PV panel > Optimiser > String > Invertor > POC > …...> Main incomer to building
As Fitted Electrical - New Panels provided and controls
Commissioning certificates - All Systems
NICEIC Electrical Certificate - or equivalent
MCS Certificate if < 50kW
Inverter Settings (Recorded)
Mechanical Schedule of Components
Electrical Schedule of Components
Routine and Emergency Operating Procedures
Routine Maintenance Requirements
Basic Fault Finding Chart
Warranty Information (register)
Manufacturers Literature (data sheets )
Remote Monitoring App
User Accounts Setup, Appoint owner, register stakeholders
Access Location and Demonstration
Agree any further routine monitoring and reaction by contractor
Functional Completion - agree stage with contractor and PM
Defects & Snagging
Agree defects list and resolution plan include timescales, to be signed off on completion and verification
Post Works - Photo condition survey of work areas and install
7 | System Use | Performance Monitoring
M&V plan, report and performance sign off of system meeting minimum operational performance requirement (consider annual review)
Who and how long for + options to Extend
Maintenance
Hand over to who + maintenance sign off + warranty options to extend + critical parts and supplier contact details
Remote Monitoring platform
Owner of monitoring , system sign in and administrator, renewal costs and options to extend
SEG - Register for SEG (annual application) or initiate export to 3rd party under PPA